## D1_Mechanical_Deployment_BOM
Component | Specification | Qty | Status | Classification | Action
Carbon Fibre Tube | 10 mm OD × 8 mm ID × 1000 mm | 4 | REMAINING | VANA Mechanical | Procure
Carbon Fibre Sheet | 300 × 200 × 2 mm | 3 | REMAINING | VANA Mechanical | Procure
Carbon Fibre Plate | 300 × 200 × 3 mm | 1 | EXISTING / VERIFY | VANA Mechanical | Physically verify
Aluminium C Clamp | 10 mm CF tube clamp | 16 | REMAINING | VANA Mechanical | Procure
Anti-Vibration Mount | APM/KK/MWC/PixHawk type | 1 | REMAINING | Vibration isolation | Procure + verify
EVA Foam Tape | 50 mm × 5 m | 1 | REMAINING | Protection | Procure
VHB / 3M Tape | High-strength mounting tape | 1 | REMAINING | Assembly | Procure
Kapton Tape | Polyimide tape | 1 | REMAINING | Insulation | Procure
CF Adhesive Tape | Waterproof adhesive tape | 1 | REMAINING | Protection | Procure
Thermal Tape | Adhesive thermal tape | 1 | REMAINING | Thermal | Procure
Wire Harness Tape | Automotive electrical protection | 2 | REMAINING | Cable protection | Procure
Nylon Cable Ties | 150 mm, 100 pcs | 1 | EXISTING / VERIFY | Cable management | Verify stock
Waterproof Enclosure | Electronics enclosure | 1 | OPEN PROCUREMENT | Environmental protection | Select + procure
Waterproof Connectors / Glands | Field sensor connections | Set | OPEN PROCUREMENT | Sensor integration | Select + procure
Sensor / Shielded Cable | Analog / RS485 cable | As required | TO PROCURE | Sensor wiring | Determine length/type
Sensor Brackets | Sensor-specific mounting | TBD | MISSING / TBD | Sensor mounting | Finalize after physical sensor inspection
Fasteners / Spacers / Standoffs | Exact size TBD | TBD | TBD | Assembly | Determine after inspection
Battery Retention Hardware | Secure battery mounting | TBD | TBD | Power mounting | Define mounting method

## D2_Mechanical_Procurement_Statu
Item | Status | Evidence | Action | Priority
Carbon Fibre Tube | REMAINING | BOM | Procure | HIGH
Carbon Fibre Sheet | REMAINING | BOM | Procure | HIGH
Carbon Fibre Plate | EXISTING / VERIFY | Existing register | Physical verification | HIGH
C Clamps | REMAINING | 16 units in BOM | Procure | HIGH
Anti-Vibration Mount | REMAINING | BOM | Procure + verify | MEDIUM
Assembly Tapes | REMAINING | BOM | Procure | MEDIUM
Cable Ties | EXISTING / VERIFY | Existing register | Verify stock | MEDIUM
Waterproof Enclosure | OPEN PROCUREMENT | BOM | Select + procure | CRITICAL
Waterproof Connectors/Glands | OPEN PROCUREMENT | BOM | Select + procure | CRITICAL
Sensor/Shielded Cable | TO PROCURE | BOM | Determine cable requirements | HIGH
Sensor Brackets | MISSING / TBD | Not specified | Finalize after sensor inspection | HIGH
Fasteners/Spacers | TBD | Not fully specified | Measure mounting interfaces | HIGH
Battery Retention | TBD | Not specified | Define | HIGH

## D3_Sensor_Mounting_Table
Sensor | Location | Mounting Method | Bracket / Hardware | Protection | Cable Routing | Hardware Status
pH | Water-facing probe support | Clamp/support | CF tube + sensor bracket TBD | Cable/connector protection | Along support arm to enclosure | NO HARDWARE VERIFIED
Turbidity | Water-facing probe support | Clamp/support | CF tube + clamp/bracket TBD | Protect cable/connector | Along support arm | NO HARDWARE VERIFIED
TDS | Water-facing probe support | Clamp/support | CF tube + clamp/bracket TBD | Protect cable/connector | Along support arm | NO HARDWARE VERIFIED
Dissolved Oxygen | Water-facing probe support | Dedicated support | CF tube + bracket TBD | Connector/cable protection | Shielded cable to enclosure | HARDWARE VERIFY
DS18B20 | Water-facing temperature point | Retainer/clamp | CF tube/plate support | Waterproof probe/interface | Along support arm | VERIFY
GNSS / Holybro M10 | Upper/exposed position | Plate/bracket mount | CF plate + bracket TBD | Protect cable/electronics | Into enclosure | VERIFY
BME280 | Protected upper area | Plate/standoff | CF plate + standoff TBD | Protect from direct water/mud | Internal cable | RECOMMENDED / VERIFY
UV Sensor | Upper/exposed area | Plate/bracket | CF plate + bracket TBD | Protect cable/connector | To enclosure | OPTIONAL
Water Level Sensor | Water-facing area | Probe support | CF tube + bracket TBD | Waterproof interface | Along support arm | OPTIONAL / TBD

## D4_Mechanical_Assembly_Plan
Step | Assembly Stage | Activity | Acceptance Check | Status
1 | Mechanical Frame | Inspect CF structural components | No damage; interfaces identified | PENDING
2 | Mounting Plates | Install CF plates/sheets | Secure and serviceable | TBD
3 | Sensor Supports | Install CF tubes + C clamps | Rigid support | TBD
4 | Vibration Isolation | Install anti-vibration mount | Secure isolation | REMAINING
5 | Sensor Mounting | Mount physically available/selected sensors | Orientation + clearance confirmed | TBD
6 | Electronics | Mount Pi, MCU and interfaces | Secure + accessible | TBD
7 | Battery / Power | Secure battery/BMS/power | Battery cannot shift | TBD
8 | Wiring | Route sensor/power/communication cables | No chafing/pinching | TBD
9 | Protection | Install enclosure/glands/connectors | Protection complete | BLOCKED — PROCUREMENT
10 | Inspection | Perform mechanical inspection | All interfaces secure | PENDING
11 | Field Readiness | Handling/disassembly check | Deployment-ready | NOT VERIFIED

## D5_Physical_Deployment_Layout
Zone | Components | Arrangement | Mechanical Requirement | Current Status
Upper / Exposed | GNSS, optional UV | Upper plate | Clear antenna/sensing area | CONCEPTUAL
Water-facing Sensor Arm | pH, DO, turbidity, TDS, DS18B20 | CF tube/clamp structure | Rigid support + probe clearance | CONCEPTUAL
Electronics Zone | Raspberry Pi, AI HAT, MCU, interfaces | Protected central enclosure | Secure mounting + service access | TBD
Power Zone | Battery, BMS, DC-DC | Secured area | Mechanical retention | TBD
Cable Route | Sensor/power/communication cables | Along CF structure | Prevent chafing/pinching | TBD
Enclosure Interface | Cable glands/connectors | Protected entry points | Water/dust protection | OPEN PROCUREMENT

## D6_Missing_Hardware_List
Missing Hardware | Why Required | Status | Priority
Waterproof Electronics Enclosure | Protect electronics during field deployment | OPEN PROCUREMENT | 🔴 CRITICAL
Waterproof Connectors/Glands | Protect sensor cable interfaces | OPEN PROCUREMENT | 🔴 CRITICAL
Sensor / Shielded Cable | Analog/RS485 connections | TO PROCURE | 🔴 HIGH
Sensor-specific Brackets | Secure pH/DO/turbidity/TDS/etc. | TBD | 🔴 HIGH
Fasteners | Secure mechanical structure | TBD | HIGH
Spacers/Standoffs | Electronics mounting | TBD | HIGH
Battery Retention Hardware | Prevent battery movement | TBD | HIGH
MAX485 / RS485 Interface | DO sensor integration | TO PROCURE / VERIFY | HIGH
RS485 Termination + TVS | RS485 protection | TO PROCURE / VERIFY | HIGH
4.7 kΩ Pull-up | DS18B20 interface | REQUIRED | HIGH
External ADC | Possible analog sensor requirement | ENGINEERING DECISION | MEDIUM

## D7_Mechanical_Readiness
Subsystem | Procured | Present | Suitable | Mounted | Assembled | Deployment Ready
CF Tube | ❌ | VERIFY | TBD | ❌ | ❌ | ❌
CF Sheet | ❌ | VERIFY | TBD | ❌ | ❌ | ❌
CF Plate | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
C Clamps | ❌ | VERIFY | TBD | ❌ | ❌ | ❌
Anti-Vibration Mount | ❌ | VERIFY | TBD | ❌ | ❌ | ❌
pH Hardware | ❌ | NO HARDWARE VERIFIED | ❌ | ❌ | ❌ | ❌
Turbidity Hardware | ❌ | NO HARDWARE VERIFIED | ❌ | ❌ | ❌ | ❌
TDS Hardware | ❌ | NO HARDWARE VERIFIED | ❌ | ❌ | ❌ | ❌
DO Hardware | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
DS18B20 | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
GNSS | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
BME280 | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
Raspberry Pi / Controller | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
Battery / Power | VERIFY | VERIFY | TBD | ❌ | ❌ | ❌
Waterproof Enclosure | ❌ | ❌ | TBD | ❌ | ❌ | ❌
Waterproof Connectors/Glands | ❌ | ❌ | TBD | ❌ | ❌ | ❌
Sensor Cable | ❌ | VERIFY | TBD | ❌ | ❌ | ❌
Final Assembly | ❌ | ❌ | ❌ | ❌ | ❌ | ❌

## D8_Mechanical_Risks
ID | Risk / Gap | Status | Evidence Boundary | Required Action
W6-2 | Quality-state routing ruling not frozen | PROVISIONAL | Software/process evidence only | Wait for Arya's ruling to be frozen
W6-3 | Fixed-ground truthful emission blocker | OPEN BLOCKER | TEST-ONLY | Resolve blocker before truthful ground emission
F001 | Ground/mechanics fixture | TEST-ONLY | No real pH/hardware evidence | Keep isolated from physical deployment claims
P1 | pH/mechanics test path | TEST-ONLY | No real pH hardware evidence | Do not claim physical sensor validation
Validator | Malformed-location handling issue | OPEN | Validator issue remains unresolved | Do not mark fixed
N3 | semantic_errors() shared crash | OPEN | Wrapper rejection is defensive handling only | Validator itself still requires resolution
N4 | G3-EXT-* prefix misuse | TEST RESULT | Specifically prefix misuse rejection | Do not generalize to unknown-device validation
N5 | Idempotency-key stability | TEST RESULT | Idempotency-key behavior only | No Group 1 replay/duplicate-prevention claim
BOM ↔ Adapter | Procurement/reference traceability | REFERENCE ONLY | Does not prove hardware connection/calibration/readings | Keep separate from physical evidence
Supporting electronics | BOM/procurement evidence | REFERENCE ONLY | Does not establish sensor deployment | Require actual hardware evidence
Analog sensors | Physical hardware evidence | NOT VERIFIED | No BOM/software proof of connection/calibration | Verify actual hardware separately
Item | Final Status / Wording
Overall Software Test Result | 11/11 software checks passed
Hardware Validation | NOT CLAIMED
Physical Sensor Validation | NOT ESTABLISHED