## D1_Mechanical_Deployment_BOM
Component | Specification | Qty | Unit Price (₹) | Total Price (₹) | Vendor | Procurement Link / Source | Status | Classification | Action
Carbon Fibre Tube | 3K roll-wrapped; 10 mm OD × 8 mm ID × 1000 mm | 4 | 1,185 | 4,740 | Existing procurement source | Existing register | REMAINING | VANA Mechanical | Procure
Carbon Fibre Sheet | 300 × 200 × 2 mm | 3 | 3,213 | 9,639 | Existing procurement source | Existing register | REMAINING | VANA Mechanical | Procure
Carbon Fibre Plate | 300 × 200 × 3 mm | 1 | Existing register | — | Existing Group 3 procurement | Existing register | EXISTING / VERIFY | VANA Mechanical | Physical fit/inventory verification
Aluminium C Clamp | 10 mm carbon-fibre tube clamp | 16 | 167 | 2,672 | Existing procurement source | Existing register | REMAINING | VANA Mechanical | Procure
Anti-Vibration Mount | UG LAND INDIA APM/KK/MWC/PixHawk type | 1 | 499 | 499 | Existing procurement source | Existing register | REMAINING | Vibration isolation | Procure + verify
EVA Foam Tape | 50 mm × 5 m | 1 | 102 | 102 | Existing procurement source | Existing register | REMAINING | Protection | Procure
VHB / 3M Tape | High-strength mounting tape | 1 | 352 | 352 | Existing procurement source | Existing register | REMAINING | Assembly | Procure
Kapton Tape | Polyimide insulation/protection tape | 1 | 624 | 624 | Existing procurement source | Existing register | REMAINING | Protection | Procure
Carbon Fibre Adhesive Tape | Waterproof structural/electronics mounting | 1 | 239 | 239 | Existing procurement source | Existing register | REMAINING | Assembly/protection | Procure
Thermal Tape | Adhesive thermal interface material | 1 | 799 | 799 | Existing procurement source | Existing register | REMAINING | Thermal interface | Procure
Wire Harness Tape | Automotive electrical protection | 2 | 426 | 852 | Existing procurement source | Existing register | REMAINING | Cable protection | Procure
Nylon Cable Ties | 150 mm, 100-piece pack | 1 pack | Existing register | — | Existing Group 3 procurement | Existing register | EXISTING / VERIFY | Cable management | Verify stock
Waterproof Enclosure | IP-rated enclosure for electronics and sensor interface | 1 | Quotation required | — | Vendor TBD | Vendor TBD | OPEN PROCUREMENT | Environmental protection | Deployment blocker until procurement is closed
Waterproof Cable Glands | IP67/IP68; sized to sensor cables | Set | Allowance | — | Vendor TBD | Vendor TBD | OPEN PROCUREMENT | Environmental protection | Select after physical/interface inspection
Waterproof Connectors | IP67/IP68 field connectors | Set | Allowance | — | Vendor TBD | Vendor TBD | OPEN PROCUREMENT | Sensor interface protection | Select after connector/cable review
Sensor Cable / Shielded Cable | Field-grade cable for analog/RS485 sensor connections | As required | Allowance | — | Vendor TBD | Vendor TBD | TBD | Cable routing | Confirm actual cable count/length with Dhruv
Sensor-specific Brackets | Mounting hardware for pH/Turbidity/TDS/DO/DS18B20 as applicable | TBD | TBD | TBD | TBD | TBD | TBD | Sensor mounting | Finalize after physical/interface inspection
Fasteners / Spacers / Standoffs | Exact size/interface TBD | TBD | TBD | TBD | TBD | TBD | TBD | Assembly | Finalize after physical/interface inspection
Battery Retention Hardware | Secure battery/BMS physically | TBD | TBD | TBD | TBD | TBD | TBD | Power mounting | Finalize after battery dimensions are confirmed

## D2_Mechanical_Procurement_Statu
Item | Latest BOM Status | Evidence | Action | Priority
Carbon Fibre Tube | REMAINING | Latest VANA BOM | Procure | HIGH
Carbon Fibre Sheet | REMAINING | Latest VANA BOM | Procure | HIGH
Carbon Fibre Plate | EXISTING / VERIFY | Latest VANA BOM | Physical fit/inventory verification | HIGH
Aluminium C Clamp | REMAINING | Latest VANA BOM | Procure | HIGH
Anti-Vibration Mount | REMAINING | Latest VANA BOM | Procure + physical verification | MEDIUM
EVA Foam Tape | REMAINING | Latest VANA BOM | Procure | MEDIUM
VHB / 3M Tape | REMAINING | Latest VANA BOM | Procure | MEDIUM
Kapton Tape | REMAINING | Latest VANA BOM | Procure | MEDIUM
Carbon Fibre Adhesive Tape | REMAINING | Latest VANA BOM | Procure | MEDIUM
Thermal Tape | REMAINING | Latest VANA BOM | Procure | MEDIUM
Wire Harness Tape | REMAINING | Latest VANA BOM | Procure | MEDIUM
Nylon Cable Ties | EXISTING / VERIFY | Latest VANA BOM | Verify inventory | MEDIUM
Waterproof Enclosure | OPEN PROCUREMENT | Latest VANA BOM | Select/procure before field deployment | CRITICAL
Waterproof Cable Glands | OPEN PROCUREMENT | Latest VANA BOM | Select after interface inspection | CRITICAL
Waterproof Connectors | OPEN PROCUREMENT | Latest VANA BOM | Select after connector/cable review | CRITICAL
Sensor / Shielded Cable | TBD | Latest VANA BOM | Confirm actual cable lengths/count | HIGH
Sensor Brackets | TBD | Interface inspection pending | Finalize after physical dimensions | HIGH
Fasteners / Spacers / Standoffs | TBD | Interface inspection pending | Finalize after measurements | HIGH
Battery Retention Hardware | TBD | Battery dimensions pending | Finalize retention method | HIGH

## D3_Sensor_Mounting_Table
Sensor | Location | Mounting Method | Bracket / Hardware | Protection | Cable Routing | Hardware Status | Dhruv Handoff / Interface Input
pH | Water-facing probe support | Clamp/support | CF tube + sensor bracket TBD | Cable/connector protection | Cable length/routing TBD | NO HARDWARE VERIFIED | Actual dimensions; mounting orientation; connector/cable count; cable routing
Turbidity | Water-facing probe support | Clamp/support | CF tube + sensor bracket TBD | Cable/connector protection | Cable length/routing TBD | NO HARDWARE VERIFIED | Actual dimensions; mounting orientation; connector/cable count; cable routing
TDS | Water-facing probe support | Clamp/support | CF tube + sensor bracket TBD | Cable/connector protection | Cable length/routing TBD | NO HARDWARE VERIFIED | Actual dimensions; mounting orientation; connector/cable count; cable routing
Dissolved Oxygen (DYS-1) | Water-facing probe support | Dedicated support | DYS-1 bracket/interface PROVISIONAL | Connector/cable protection | Cable length/routing TBD | VERIFY | Actual dimensions; mounting orientation; connector/cable count; routing; confirm DYS-1 interface
DS18B20 | Water-facing temperature point | Retainer/clamp | CF tube/plate support; retainer TBD | Cable/connector protection | Cable length/routing TBD | VERIFY | Actual dimensions; mounting orientation; connector/cable count; routing
GNSS / Holybro M10 | Upper/exposed position | Plate/bracket mount | CF plate + bracket TBD | Protect cable/electronics | Cable length/routing TBD | VERIFY | Actual dimensions; antenna placement/orientation; connector/cable count; routing
BME280 | Protected upper area | Plate/standoff | CF plate + standoff TBD | Protect from direct water/mud | Cable routing TBD | RECOMMENDED / CONDITIONAL | Confirm if selected; actual dimensions/interface
UV Sensor (GUVA-S12SD) | Upper/exposed area if mission requires | Plate/bracket | CF plate + bracket TBD | Cable/connector protection | Cable routing TBD | OPTIONAL / MISSION-DEPENDENT | Confirm only if selected
Water Level/Depth Sensor | Water-facing area if mission requires | Probe support | CF tube + bracket TBD | Waterproof interface | Cable routing TBD | OPTIONAL / MISSION-DEPENDENT | Confirm only if selected
Camera / Oak-D Pro | Mission-dependent protected/exposed camera position | Bracket/interface TBD | Camera-specific bracket TBD | Protect connector/cable; no unsupported weather/IP claim | Cable length/routing TBD | HARDWARE-FACING CODE ONLY; PHYSICAL CAPTURE NOT EVIDENCED | Confirm actual camera dimensions, mounting orientation, connector/cable count and physical placement if deployed

## D4_Mechanical_Assembly_Plan
Step | Assembly Stage | Activity | Acceptance Check | Status
1 | Mechanical Frame | Inspect structural frame and CF components | Physical condition and interfaces identified | PENDING
2 | Mounting Plates | Install CF plates/sheets | Physical fit secure; serviceable | PENDING
3 | Sensor Supports | Install CF tubes + C clamps | Rigid physical support; dimensions/interfaces fit | PENDING
4 | Vibration Isolation | Install anti-vibration mount | Physical mount secure | REMAINING
5 | Sensor Mounting | Mount pH/Turbidity/TDS/DO/DS18B20 interfaces as selected | Physical fit, orientation and clearance only; no functionality/calibration claim | PENDING
6 | Electronics | Mount Pi/MCU/interfaces and camera hardware if selected | Physical fit/interface secure and accessible | PENDING
7 | Battery / Power | Secure battery/BMS/power | Battery physically retained after dimensions/interface confirmation | TBD
8 | Wiring | Route sensor/power/communication cables | No chafing/pinching; routing confirmed after actual cable lengths | TBD
9 | Protection | Install enclosure + glands + connectors | Enclosure/glands procured, installed and interface checked | BLOCKED — OPEN PROCUREMENT
10 | Inspection | Perform mechanical inspection | Actual physical assembly and inspection evidence exists | PENDING
11 | Field Deployment | Complete physical assembly and readiness inspection | Deployment-ready evidence exists | NOT VERIFIED

## D5_Physical_Deployment_Layout
Zone | Components | Arrangement | Mechanical Requirement | Current Status
Upper / Exposed | GNSS / Holybro M10; optional UV | Upper plate | Clear antenna/sensing area; antenna placement must be physically confirmed | VERIFY
Water-facing Sensor Arm | pH, Turbidity, TDS, DO, DS18B20 | CF tube/clamp structure | Rigid support + probe clearance + physical interface fit | VERIFY / TBD
Atmospheric / Protected Zone | BME280 if selected | Protected plate/standoff area | Protect from direct water/mud; final placement conditional | RECOMMENDED / CONDITIONAL
Camera / Vision Zone | Oak-D Pro / camera if mission requires | Dedicated camera bracket; orientation TBD | Physical dimensions/interface and cable routing must be confirmed | VERIFY IF DEPLOYED
Electronics Zone | Raspberry Pi 5, AI HAT+ 2, MCU, interfaces | Protected central enclosure | Physical fit + service access | TBD / OPEN
Power Zone | Battery, BMS, DC-DC | Secured area | Battery dimensions + retention hardware required | TBD / OPEN
Cable Route | Sensor/power/communication cables | Along CF structure and into enclosure | Actual cable lengths/counts required; prevent chafing/pinching | TBD / OPEN
Enclosure Interface | Waterproof enclosure + glands/connectors | Protected cable entry points | Selection/procurement required before deployment | OPEN PROCUREMENT — DEPLOYMENT BLOCKER
Dhruv Handoff | Sensor dimensions, mounting orientation, connector/cable count, cable routing, enclosure/environment rating, battery dimensions | Required inputs before final physical layout | Physical/interface inspection only | OPEN

## D6_Missing_Hardware_List
Missing / Open Mechanical Hardware | Why Required | Status | Priority
Waterproof Electronics Enclosure | Protect electronics and sensor interfaces during field deployment | OPEN PROCUREMENT | CRITICAL
Waterproof Cable Glands | Protected cable entry into enclosure | OPEN PROCUREMENT | CRITICAL
Waterproof Connectors | Removable field sensor connections | OPEN PROCUREMENT | CRITICAL
Sensor / Shielded Cable | Field-grade analog/RS485 cable routing | TBD | HIGH
Sensor-specific Brackets | Secure current environmental sensor interfaces | TBD | HIGH
Fasteners | Secure structural and mounting hardware | TBD | HIGH
Spacers / Standoffs | Mount plates/electronics as required | TBD | HIGH
Battery Retention Hardware | Prevent battery movement | TBD | HIGH
DYS-1 Bracket / Interface Hardware | Depends on actual DYS-1 dimensions/interface | PROVISIONAL — Dhruv confirmation required | HIGH
Cable-management Hardware | Depends on actual cable count/length/routing | TBD | MEDIUM

## D7_Mechanical_Readiness
Subsystem | Procured | Present | Suitable* | Mounted | Assembled | Deployment Ready
CF Tube | ❌ | VERIFY | TBD — physical fit/inventory only | ❌ | ❌ | ❌
CF Sheet | ❌ | VERIFY | TBD — physical fit/inventory only | ❌ | ❌ | ❌
CF Plate | VERIFY | VERIFY | TBD — physical fit/inventory only | ❌ | ❌ | ❌
C Clamps | ❌ | VERIFY | TBD — physical fit/interface only | ❌ | ❌ | ❌
Anti-Vibration Mount | ❌ | VERIFY | TBD — physical fit only | ❌ | ❌ | ❌
pH Hardware | ❌ | NO HARDWARE VERIFIED | NOT VERIFIED | ❌ | ❌ | ❌
Turbidity Hardware | ❌ | NO HARDWARE VERIFIED | NOT VERIFIED | ❌ | ❌ | ❌
TDS Hardware | ❌ | NO HARDWARE VERIFIED | NOT VERIFIED | ❌ | ❌ | ❌
DO / DYS-1 | ❌ | VERIFY | TBD — physical fit/interface only | ❌ | ❌ | ❌
DS18B20 | ❌ | VERIFY | TBD — physical fit/interface only | ❌ | ❌ | ❌
GNSS / Holybro M10 | VERIFY | VERIFY | TBD — physical fit/antenna placement only | ❌ | ❌ | ❌
BME280 | ❌ | VERIFY | TBD — physical fit/interface only | ❌ | ❌ | ❌
Camera / Oak-D Pro | VERIFY IF DEPLOYED | NOT PHYSICALLY EVIDENCED HERE | TBD — physical fit/interface only | ❌ | ❌ | ❌
Raspberry Pi / Controller | VERIFY | VERIFY | TBD — physical fit/interface only | ❌ | ❌ | ❌
Battery / Power | VERIFY | VERIFY | TBD — physical fit/retention only | ❌ | ❌ | ❌
Waterproof Enclosure | ❌ | ❌ | TBD | ❌ | ❌ | ❌
Waterproof Connectors/Glands | ❌ | ❌ | TBD | ❌ | ❌ | ❌
Sensor Cable | ❌ | VERIFY | TBD — routing/interface only | ❌ | ❌ | ❌
Final Assembly | PENDING | PENDING | PENDING | PENDING | PENDING | NOT VERIFIED
Field Readiness Evidence | PENDING | PENDING | Physical fit/assembly inspection only | PENDING | PENDING | NOT VERIFIED

## D8_Mechanical_Risks
ID | Risk / Dependency | Status | Evidence Boundary | Required Action
W6-2 | Quality-state routing ruling not frozen | PROVISIONAL | Not canonical | Wait for Arya's ruling to be frozen
W6-3 | Fixed-ground truthful emission blocker | OPEN BLOCKER / TEST-ONLY | No truthful ground emission | Resolve blocker before truthful ground emission
F001 | Ground/mechanics fixture | TEST-ONLY / MECHANICS-ONLY | No real pH/hardware claim | Keep isolated from physical deployment evidence
P1 | pH/mechanics test path | TEST-ONLY / MECHANICS-ONLY | No real pH hardware claim | Keep isolated from physical deployment evidence
N3 | Shared semantic_errors() crash | OPEN | Wrapper rejection is defensive handling, not validator fix | Keep validator issue open
N4 | G3-EXT-* prefix misuse rejection | TEST RESULT | Specific prefix misuse rejection only | Do not generalize to unknown-device validation
N5 | Idempotency-key stability | TEST RESULT | Idempotency-key stability only | No Group 1 replay/duplicate-prevention claim
Validator | Malformed-location handling issue | OPEN | Not fixed | Do not mark resolved
BOM ↔ Adapter | Procurement/reference traceability | REFERENCE ONLY | Does not prove hardware connection, calibration or field readings | Keep separate from physical evidence
CONTROLLED / is_synthetic=True | Test/reference state | TEST / REFERENCE ONLY | Never physical deployment evidence | Do not use as physical evidence
Dhruv-01 | Actual sensor dimensions | OPEN | Physical/interface input only | Obtain dimensions before final bracket/layout selection
Dhruv-02 | Mounting orientation | OPEN | Physical/interface input only | Confirm orientation for each selected sensor
Dhruv-03 | Connector/cable count | OPEN | Physical/interface input only | Confirm connector types/counts and cable lengths
Dhruv-04 | Cable routing | OPEN | Physical/interface input only | Finalize route after actual cable lengths are known
Dhruv-05 | Enclosure/environment rating | OPEN | Procurement/interface evidence only | Confirm requirement; do not claim unsupported IP/weather rating
Dhruv-06 | Battery dimensions | OPEN | Physical/interface input only | Confirm dimensions before retention design
DYS-1 | DYS-1 bracket/interface | PROVISIONAL | Physical/interface pending Dhruv | Confirm actual dimensions/interface
Holybro M10 | GNSS mounting/antenna placement | VERIFY | Physical fit/antenna placement only | Confirm actual physical/antenna placement
Enclosure/Glands | Waterproof enclosure + glands | OPEN PROCUREMENT | Deployment blocker | Close procurement before Step 9 / field deployment
Camera | Oak-D Pro capture code | HARDWARE-FACING CODE ONLY | Code uses real depthai SDK; no physical capture evidence from uploaded files alone | Run on physically connected camera and retain capture evidence before claiming hardware evidence
Software Result | 11/11 software checks passed | SOFTWARE TEST RESULT ONLY | No hardware/physical/calibration evidence | Keep separate from mechanical readiness
Mechanical Suitable | Definition | PHYSICAL FIT / INTERFACE ONLY | Does not mean functionality, calibration or field readiness | Use this meaning consistently
Field Readiness | Actual physical assembly + inspection | NOT VERIFIED | No deployment evidence yet | Complete assembly, inspection and evidence

## Final_Notes
Final Control / Evidence Boundary | Status
Latest BOM mechanical status | CF tube/sheet/clamps = REMAINING; CF plate = EXISTING / VERIFY; enclosure/glands = OPEN PROCUREMENT; brackets/fasteners/spacers/battery retention = TBD
Environmental mechanical interfaces | pH / Turbidity / TDS / DO / DS18B20 remain current environmental mechanical interfaces
Optional/conditional sensors | BME280 = RECOMMENDED / CONDITIONAL; UV and Water Level = OPTIONAL / MISSION-DEPENDENT
Holybro M10 | VERIFY until physical/antenna placement is confirmed
DYS-1 | Bracket/interface PROVISIONAL until Dhruv confirms actual dimensions/interface
Dhruv handoff | Actual sensor dimensions; mounting orientation; connector/cable count; cable routing; enclosure/environment rating; battery dimensions
W6-2 | PROVISIONAL — quality_state routing is not canonical until ruling is frozen
W6-3 / F001 / P1 | TEST-ONLY; W6-3 remains OPEN BLOCKER; no truthful ground emission or real pH/hardware claim
Malformed-location validator issue | OPEN — do not claim fixed
BOM ↔ Adapter | PROCUREMENT / REFERENCE EVIDENCE ONLY
CONTROLLED / is_synthetic=True | TEST / REFERENCE STATE ONLY
Oak-D Pro files | Hardware-facing real SDK code; absence of a physical capture result in the supplied files means no physical deployment claim
11/11 | SOFTWARE TEST RESULT ONLY
Mechanical verification | Physical fit / inventory / interface verification only; not functionality, calibration or field readiness
Final assembly / Field readiness | PENDING / NOT VERIFIED until actual assembly, inspection and evidence exist
Source update | Latest VANA BOM, VANA BOM & procurement list, previous mechanical workbook, and newly supplied Oak-D/observation files
BOM evidence | Latest BOM explicitly marks enclosure and connectors/glands OPEN PROCUREMENT and mechanical items as REMAINING / EXISTING-VERIFY as applicable.
Oak-D evidence | The supplied capture script states it talks to a physically connected Oak-D Pro and fails honestly if no device is connected; this is code evidence, not proof that a capture has actually been performed.