GROUP 3 — HARDWARE, ROBOTICS & EDGE

DAY 1 · END-OF-DAY PROCESS REPORT

2026-08-11   |   Today's Lead: Suraj Surve   |   Observation Lead: Hemanth Reddy

Contributors: Arya Barge · Manya Shukla · Dhruv Patel · Hemanth Reddy · Ashmit Pandey

Mission gate:  Exists → Powers on/runs → Interfaces → Produces measurable output → Telemetry captured → Integrates → Reusable

# 0.  EXECUTIVE SUMMARY

Today produced the first photographic evidence of physical hardware in Group 3's history. Manya supplied 14 photographs of 3D-printed structural components, backed by a formal Mechanical & Structural Verification matrix and a corrected inventory. That moves her prototype from reported to EVIDENCED.

No system reached "Powers on / runs." Both quadrupeds are pre-assembly: 0 of 8 actuators on either. Per Suraj: "They both are in their initial stage. Testing needs to happen post 3D print assembly."

The runtime side reached "Produces measurable output + Telemetry captured" with captured evidence — a live fail-closed enforcement gate, 165 passing tests, and a real reasoning decision.

Group 3's honest position tonight: verified physical parts (not an assembled machine), a verified software runtime (not connected to hardware), and a precisely quantified shortfall between them.

| Gate | Manya's prototype | Arya's prototype | Dhruv's control path | Hemanth's runtime |
| --- | --- | --- | --- | --- |
| 1 Exists | YES — photo-verified parts | CAD only | Electronics NOT finalised | YES |
| 1b Assembles / articulates | NO — Not Assembled | NO | — | — |
| 2 Powers on / runs | NO — 0/8 actuators | NO — 0/8 actuators | NO | YES |
| 3 Interfaces | NO | NO | documented only | YES — verified live |
| 4 Measurable output | NO | NO | external dataset | YES — captured |
| 5 Telemetry captured | NO | NO | external dataset | YES — captured |
| 6 Integrates | NO | NO | NO | NO — contract-only |
| 7 Reusable | Potentially | Potentially | — | YES (software) |

# 1.  WHAT EACH MEMBER DELIVERED

## 1.1  Suraj — Hardware/Robotics System Convergence

| Assignment item | Delivered | Status |
| --- | --- | --- |
| Coordinate complete Group 3 verification | Ran the day; corrections issued 08:05 | DONE |
| Establish current status of each capability | Ruled: two separate prototypes, both initial-stage | DONE |
| Identify systems with working hw/fw/sw/control | Established none past 3D-print assembly | DONE |
| Drive one complete system-level proof | NOT ACHIEVED on hardware — no actuators exist | BLOCKED (correctly) |
| Maintain morning + EOD updates | Morning direction + 1108 report consolidation | DONE |
| Consolidate blockers and dependencies | Assigned electronics ownership to Dhruv | DONE |

Decisions issued today:

08:05 — H Frame → 3D print required; M2.5 nuts → hardware procurement, not 3D print

Two prototypes ruling — M2.5 correct for Manya's SCALED print model

Verification target — check mechanical linkages on printed parts; motors/actuators not required

Stage clarification — both prototypes initial-stage; testing post 3D-print assembly

Electronics ownership assigned to Dhruv

## 1.2  Manya — Mechanical / Structural / Actuation Verification    [STRONGEST EVIDENCE TODAY]

| Assignment item | Delivered | Status |
| --- | --- | --- |
| Verify structural/mechanical/actuation components | Mechanical & Structural Verification matrix — 16 rows, 8 columns | DONE |
| Validate load/actuation assumptions vs hardware | "After test NA" — correctly deferred; no actuators to test | HONESTLY DEFERRED |
| Document component interfaces and constraints | Constraints recorded: H-frame size, print time | DONE |
| Identify reusable modules vs prototype-specific | Every row classified. Leg Assembly = PROTOTYPE ONLY | DONE — answers the mission question |
| Provide evidence of actual operation | 14 PHOTOGRAPHS of printed components | DONE — first physical evidence in the group |

She also corrected her own inventory beyond what Suraj asked — two changes nobody requested: Smaller Disc 4→0 (to be printed), lower link 4→2. Self-correction without prompting is the strongest process signal of the day.

## 1.3  Dhruv — Telemetry / Control / Execution Integration

| Assignment item | Delivered | Status |
| --- | --- | --- |
| Verify actual control/execution path | "NA" | CORRECTLY RECORDED AS NA |
| Establish command → controller → actuator → telemetry | Dataset picked from online (torque etc.); telemetry ready via py code | Code exists; data is EXTERNAL, not from the robot |
| Verify state propagation, APIs/interfaces | "NA" | CORRECTLY RECORDED |
| Capture runtime logs and telemetry evidence | Dataset evidence based on AI leverage | NOT runtime evidence from the assigned system |
| Identify what connects to BHIV execution/observability | Live integration post testing on both prototypes | Deferred, correctly |
| Reported a provisional control path | RPi 4 + PCA9685 + 8x MG996R; RPi4 → I2C → PCA9685 → PWM → MG996R | PROVISIONAL — electronics not finalised. Final BOM follows body completion |

Recorded fairly: Dhruv wrote "NA" three times rather than claiming partial success — non-negotiable #2 applied to his own work. His telemetry code is real; the data exercising it is an online dataset, not robot telemetry, which he stated plainly. No overclaim was made. He also challenged an unverified actuator claim of mine — see §6.

## 1.4  Arya — Terrain / Gait / Stability / Mechanical Integration

| Assignment item | Delivered | Status |
| --- | --- | --- |
| Verify locomotion vs existing implementation | Group consolidation records "Yet to report" | PENDING |
| Demonstrate terrain/gait/stability where hw available | No hardware available; gait sim promised by EOD | PENDING |
| Document mechanical and control interfaces | M3 fasteners confirmed from live SolidWorks assembly | DONE |
| Separate demonstrated from planned capability | Pre-labelled the sim "simulation, not a physical demonstration" — unprompted | DONE — rule-4 discipline applied voluntarily |
| Capture video and measurable runtime evidence | 4 CAD assembly views shared; gait video pending | PENDING |

Note on her four images: they are SolidWorks CAD renders, not photographs (title bars show SOLIDWORKS/MBD/RoboDK; status "Under Defined · Editing Assembly"; Motion Study 1 tab present). This is NOT a misrepresentation — for a terrain/gait assignment, CAD plus a motion study is the correct artifact and she labelled it correctly in advance. Recorded because rule 1 distinguishes a model from a physical object.

## 1.5  Ashmit — Evidence / Capability Packaging

| Assignment item | Delivered | Status |
| --- | --- | --- |
| Consolidate hardware/robotics evidence | "Unable to compile due to software restrictions" | BLOCKED — reported, not hidden |
| Track each capability V0–V4 | Not produced; scale never defined | NOT DONE |
| Record owner/status/interface/telemetry/deps/blocker | Not produced | NOT DONE |
| Prepare reusable capability packets | Redirected: packets to go direct to Suraj | REROUTED |

Recorded per rule 9 ("A failed experiment is acceptable. Hiding the failure is not"): Ashmit reported the blocker rather than going silent. The V0–V4 scale remains undefined group-wide — an open dependency, not a personal failure.

# 2.  HEMANTH — EDGE / SYSTEM ORCHESTRATION

Scope note. My brief says "map the hardware/edge systems to the wider BHIV runtime." That is both halves: the Group 3 hardware AND the BHIV runtime it must attach to. The runtime components I own — Sarathi, PIG, AQIAIC — are BHIV runtime capabilities from the Day-1 reusable inventory, so they are in scope as the DESTINATION, not as a separate project report.

## 2.1  Map the hardware/edge systems to the wider BHIV runtime

The composed path — everything except the leftmost box already exists and was verified today:

┌──────────────┐  observation   ┌──────────────┐   decision   ┌──────────┐   sealed   ┌───────────┐
 │ Vana / G3    │ ─────────────► │   AQIAIC     │ ───────────► │ Sarathi  │ ─────────► │ Bucket    │
 │ edge device  │  (+confidence  │ reason OR    │ (+ trace_id) │ enforce  │            │InsightFlow│
 │  /analyze    │   or abstain)  │   abstain    │              │  seal    │            │KARMA/PRANA│
 └──────┬───────┘                └──────┬───────┘              └────┬─────┘            └───────────┘
        │                               │                           │
        └───────────────────────────────┴───────────────────────────┘
            recorded in PIG: WorkItem · Deliverable · EvidenceReference
            append-only · bitemporal · sha256-replayable

Day-1 BHIV reusable inventory mapped against what I verified:

| BHIV capability (Day-1 list) | Verified state today | Edge relevance |
| --- | --- | --- |
| TANTRA / Sarathi | LIVE — sarathi-9n5g.onrender.com, fail-closed proven | Actuation authority for any robot command |
| Capability Registry | Exists — src/pig/runtime/capabilities/ | Register a Vana sensing capability |
| Replay | Exists — pig/replay_engine.py, tantra_replay.go | Replay recorded evidence |
| Bucket | reference-standby — adapter ready, NO live endpoint | Observation storage |
| InsightFlow | reference-standby, digest-only contract | Telemetry (never gates execution) |
| PRANA / KARMA | env-gated, NO endpoints | Behaviour signals / outcome evidence |
| GC / TMS / MDU | contract-only — opaque seams, internals unknown | Governance boundary |
| Execution Registry | 0 matches in the three repos I hold | Unknown |
| InsightBridge / InsightCore / QCG / MASTERDB | 0 matches | Unknown |
| Samachar | public catalogue = Coming Soon; AQIAIC registry = interface_only | Declared ObservationSource — the port a sensor occupies |
| SANSKAR | 16 matches, ALL the personal name "Sanskar" — no system found | — |
| UniGuru / RAG | Live publicly (uni-guru.in) | Not edge-relevant |
| Niyantran / SETU / Pravah | Published Live | Group 4 territory |

## 2.2  How commands, telemetry, device state and failures move between edge and software

| Flow | Mechanism | Verified? |
| --- | --- | --- |
| Command → device | POST /v1/enforce → 9-check verification → sealed envelope → ExecutionHandler → HTTP POST of signed CapabilityToken | Gate verified live; webhook NEVER exercised by hardware |
| Device → telemetry | /v1/observe (intake) → /v1/downstream-ack (signed receipt) | BOTH return 404 on the deployment |
| Device state | trace_id through every hop; chain_binding_hash binds every artifact | Contract verified |
| Failure | FAIL-CLOSED — verification failure halts the chain; no fall-through to allow | PROVEN LIVE |
| Observation → evidence | PIG: WorkItem + Deliverable + one EvidenceReference per reading | 165 tests pass |
| Reasoning | AQIAIC POST /decision — confidence band + honest abstention | Real decision produced |

## 2.3  Verify available communication interfaces — KEY EDGE FINDING

Probed 18 endpoints against the live deployment — every entry below was individually tested:

| LIVE and responding | Returns 404 — NOT DEPLOYED |
| --- | --- |
| /health · /health/deep (3/3 checks, router 4/4) | /v1/evaluators/* — register/challenge, register/complete, JWKS |
| /metrics · /metrics/prometheus | /v1/observe — observation intake |
| /v1/bridge/info | /v1/downstream-ack — signed receipt callback |
| /v1/enforce (POST → fail-closed) | /v1/audit |
| /v1/ingest-decision (POST → fail-closed) | /v1/handshake, /v1/handshake-peer |
| /sarathi/enforce (POST → fail-closed) | /bucket/artifacts |
| /sarathi/validate-token (GET → ERR_TOKEN_MISSING) | /v1/handshake-peer |

CONSEQUENCE: the missing routes are exactly the ones an edge device needs — onboarding (evaluator registration + JWKS for key distribution), observation intake, and acknowledgement. A Vana edge node CANNOT register against the live service today, and CANNOT close the telemetry loop.

Hypothesis, stated as hypothesis: the deployment reports service_version 8.0.0 (and 5.0.0 on deep health) while repo documentation describes v15.11 — so Render is probably running an older build. Redeploying would likely restore these routes. Not yet confirmed.

## 2.4  Dependencies on existing execution, telemetry and storage

| Dependency | State | Blocks |
| --- | --- | --- |
| Sarathi execution webhook | Built, env-switched (SARATHI_WEBHOOK_URL) | Nothing — ready |
| Device-side webhook receiver | DOES NOT EXIST | Actuation. Group 3 build item |
| Sarathi onboarding routes | 404 on deployment | Device registration |
| Bucket endpoint | No live URL | Observation persistence |
| InsightFlow endpoint | No live URL | Telemetry |
| Device identity at fleet scale | UNSOLVED — peer-key pinning suits a few servers, not many field devices | Fleet deployment. Group 4 dependency |
| AQIAIC deployment | Local only | Reasoning in production |
| PIG host process | Unowned | Evidence recording |

## 2.5  One concrete edge-to-runtime integration proof — DELIVERED

"Where possible" — hardware side impossible (no powered device exists). Runtime side proven.

PROOF 1 — Fail-closed enforcement, verified live

POST https://sarathi-9n5g.onrender.com/v1/enforce
Body: {"decision_id":"VANA-EDGE-TEST-001","action":"actuator.move",
       "payload":{"joint":"hip_fl","angle":15}}

→ HTTP 400
  {"detail":"one or more X-Sarathi-* headers missing",
   "error":"ERR_INBOUND_SIGNATURE_MISSING","issuer_id":""}

It refused. It did not fall through to allow. An unsigned actuator command was rejected by the live gate — the single most important safety property for a robot, proven on a running service rather than a diagram.

PROOF 2 — Deterministic evidence spine

python -m pytest tests -q  →  165 passed in 7.17s    ·    python demo/run_demo.py  →  completed, printing "All outputs above were produced by the real capability."

PROOF 3 — Reasoning with honest abstention

python run_engine.py examples/payloads/sell_store_with_enwr.json  →  decision dec_a24e0274030ece3735f6c31764e1907e, STORE_WITH_ENWR, confidence_band: high, confidence_score: 0.855, best 8054.1 / avg 7554.1 / worst, abstained: false.

Repo integrity: all three BHIV repos unmodified — git status --porcelain still returns the recorded baselines (24 AQIAIC, 10 PIG). Suites run with -p no:cacheprovider and PYTHONDONTWRITEBYTECODE=1.

HONEST STATUS: contract-only for hardware. Runtime half proven; device half absent.

# 3.  PHYSICAL EVIDENCE RECEIVED — Manya's printed components

14 photographs, timestamps visible in-frame (13:17 / 13:24, 11-08-2026), taken at a workstation with the inventory spreadsheet open on screen.

| Photo | Contents observed | Maps to inventory row |
| --- | --- | --- |
| WA0003 | 8 flat discs, 4 mounting holes each, visible FDM layer lines | disc(1) — 8/8 Available |
| WA0007 | 4 U-channel brackets, open-top | c-bracket type — 4/4 |
| WA0012 | 4 U-channel brackets, taller, slot/hook feature at top | second c-bracket type — 4/4 |
| WA0015 | 2 cylindrical links | lower link — 2 of 4 — EXACTLY matches corrected qty |
| WA0016 | 4 cylindrical links | link1 — 4/4 |
| WA0004–06, 08–11, 13–14 | Further component groups, same session | Supporting |

What the photographs PROVE: the printed structural components physically exist, in the quantities the corrected inventory states. WA0015 showing exactly 2 lower links — matching the self-correction from 4 → 2 — is strong internal corroboration.

What they do NOT prove: no assembly, no actuators, no powered operation. Consistent with the verification matrix, which records Leg Assembly = "Not Assembled".

Print-quality observation (neutral): visible stringing artifacts on several parts — normal FDM behaviour, cosmetic. Worth a retraction/temperature tweak before final parts, not a defect.

WA0003 — disc(1) x8, joint connection discs (8/8 available)

WA0007 — C-brackets x4, mechanical interface (4/4 available)

WA0012 — C-brackets x4, second type (4/4 available)

WA0015 — lower link x2 — matches corrected quantity 2 of 4

WA0016 — link1 x4, upper leg links (4/4 available)

Arya — CAD assembly views (recorded as CAD evidence, NOT physical hardware):

Arya — SolidWorks isometric assembly view (CAD, not a photograph)

Arya — front view; status bar reads "Under Defined · Editing Assembly"; Motion Study 1 tab present

# 4.  INVENTORY — CONSOLIDATED  (Manya's corrected inventory + verification matrix)

| Component | Category | BOM | Avail | Physical status | Assembly verif. | Test status | Evidence | Reusable |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ground Reference | Structural | 1 | 1 | To be 3D printed | Pending | Pending | Not available | Potentially |
| H Frame1 | Structural | 1 | 1 | To be 3D printed (Suraj's correction) | Pending | Pending | Not available | Potentially |
| RX_64 | Actuation | 4 | 0 | PENDING | Pending | Not physically tested | Not available | Potentially |
| c bracket | Mech. interface | 4 | 4 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| disc(1) | Structural | 8 | 8 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| link1 | Structural | 4 | 4 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| c bracket2 | Mech. interface | 4 | 4 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| RX_28 | Actuation | 4 | 0 | PENDING | Pending | Not physically tested | Not available | Potentially |
| C bracket 3 | Mech. interface | 4 | 4 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| Smaller Disc | Structural | 4 | 0 | To be 3D printed (self-corrected 4→0) | Pending | Not operationally tested | Available | Potentially |
| lower link | Structural | 4 | 2 | Available (self-corrected 4→2) | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| Foot | Structural | 4 | 4 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| M2.5 x 16 bolts | Fasteners | 96 | 96 | Available | VERIFIED | Not operationally tested | AVAILABLE | Potentially |
| M2.5 nuts | Fasteners | 96 | 0 | Hardware procurement (Suraj's correction) | Pending | Pending physical actuation | Not available | Potentially |
| Leg Assembly | Mech. assembly | — | — | NOT ASSEMBLED | Pending | Pending physical actuation | Not available | PROTOTYPE ONLY |
| Quadruped Locomotion | System capability | — | — | Simulation demonstrated | Verified | PHYSICAL RUNTIME PENDING | Not available | — |

The shortfall, precisely quantified:

| To 3D print | To procure |
| --- | --- |
| Ground Reference x1 · H Frame1 x1 · Smaller Disc x4 · lower link x2 | RX_64 x4 · RX_28 x4 · M2.5 nuts x96 |
| = 8 parts | = 8 actuators + fasteners |

Physically in hand: 30 printed components + 96 bolts.     Documented constraints (Manya): H-frame size, print time.

# 5.  NON-NEGOTIABLES — COMPLIANCE

| # | Rule | Status | Evidence |
| --- | --- | --- | --- |
| 1 | No hardware capability accepted from a diagram alone | HELD | Arya's CAD renders recorded as CAD, not hardware. Manya's photos accepted as physical because they ARE photographs |
| 2 | No "working" claim without physical/software runtime evidence | HELD | Dhruv recorded "NA" 3x. His telemetry data labelled external dataset, not robot telemetry. Sarathi graded V3 not V4 — total_routed: 0 |
| 3 | Separate hardware exists / software exists / integrated works / production-ready | HELD | §0 gate table separates all four. Hardware exists YES; integrated works NO |
| 4 | Every serious capability requires a short runtime video | NOT MET | ZERO videos exist. Manya's linkage video, Arya's gait sim, and 3 terminal captures all outstanding |
| 5 | Preserve device identity, ownership, provenance, telemetry | HELD | Every document attributed by author + timestamp; photos carry in-frame timestamps; repo HEADs + sha256 recorded |
| 6 | Do not create new hardware architecture merely to demonstrate | HELD | No new design proposed by anyone. Edge proof used EXISTING endpoints only |
| 7 | Failures, unavailable hardware, missing interfaces recorded explicitly | HELD | 8 missing Sarathi routes · 0/8 actuators · Ashmit's tooling block · Dhruv's 3x NA · 2 errors of my own — all recorded |

# 6.  PROCESS OBSERVATIONS

What went right — and it was a good day for process

Members applied the non-negotiables to each other, and to themselves.

Dhruv challenged an unverified claim of mine. I had told him Manya's RX actuators implied serial-bus telemetry and no PCA9685. He replied: "I would not claim the RX-64/RX-28 path or remove the PCA9685 based on the current BOM." He was right. That is rule 2 enforced against the observation lead — the healthiest signal today.

Manya self-corrected twice, unprompted (Smaller Disc 4→0, lower link 4→2) and produced the group's first physical evidence.

Arya pre-labelled her simulation as "simulation, not a physical demonstration" BEFORE being asked.

Ashmit reported a blocker rather than going quiet — rule 9 working as intended.

Suraj decided quickly, and his mechanical-linkage target converted an impossible task into an achievable one WITHOUT inventing new architecture (rule 6).

Errors made and corrected — including mine

| Error | By | Correction |
| --- | --- | --- |
| Read Manya's and Arya's inventories as ONE robot → reported 6 false "contradictions" | Hemanth | Two separate prototypes. 4 questions withdrawn |
| Flagged M2.5 vs M3 as a procurement risk | Hemanth | NO risk — M2.5 correct for the scaled model. Withdrawn |
| Told Dhruv the RX path meant "no PCA9685" | Hemanth | Caught by Dhruv. True only for Manya's model |
| Graded Sarathi V4 | Hemanth | V3 — total_routed: 0, no peer round-trip ever occurred |

No silent architectural change occurred. My Day-2 morning concern that the actuator had been swapped without escalation does not hold — the RX units belong to a different prototype, not a changed one.

Process gaps

Rule 4 unmet across the board — no runtime videos from anyone, including me.

V0–V4 scale never defined, so no capability was graded on the group's intended scale.

Arya's locomotion verification recorded as "Yet to report" at consolidation time.

Ashmit blocked by tooling — capability packaging did not happen; packets rerouted to Suraj.

# 7.  REQUIRED EVIDENCE CHAIN — per capability

Hardware/source → software/firmware → command/input → execution → physical/system output → telemetry/log → interface → video → integration status → blocker → reuse potential

### C-1 · Manya's RX Quadruped (structural)

| Field | Value |
| --- | --- |
| Hardware/source | 30 printed components + 96 M2.5 bolts — PHOTO-VERIFIED |
| Software/firmware | None |
| Command/input | None — no actuators |
| Execution | NOT ASSEMBLED |
| Physical output | None |
| Telemetry/log | None |
| Interface | Mechanical only; RX_64/RX_28 mounts (unpopulated) |
| Video | PENDING |
| Integration status | Not started |
| Blocker | 8 actuators · 8 parts to print · 96 nuts to procure |
| Reuse potential | Potentially reusable (Manya's classification); Leg Assembly = Prototype Only |

### C-2 · Manya's Quadruped Locomotion (capability)

| Field | Value |
| --- | --- |
| Hardware/source | None |
| Software/firmware | SolidWorks Motion Analysis, RX configuration |
| Command/input | Simulated gait |
| Execution | SIMULATION DEMONSTRATED — flat, inclined, declined |
| Physical output | PHYSICAL RUNTIME PENDING |
| Telemetry/log | None |
| Interface | CAD/simulation only |
| Video | PENDING |
| Integration status | Not started |
| Blocker | No actuators |
| Reuse potential | Simulation methodology reusable; NOT a demonstrated physical capability |

### C-3 · Arya's BOM Quadruped

| Field | Value |
| --- | --- |
| Hardware/source | None built — CAD assembly only |
| Software/firmware | None |
| Command/input | None |
| Execution | — |
| Physical output | — |
| Telemetry/log | — |
| Interface | M3 fasteners CONFIRMED from live assembly; I2C · DVP+SCCB · 8x PWM · Wi-Fi/BLE (designed) |
| Video | Gait sim promised EOD, pre-labelled simulated |
| Integration status | Not started |
| Blocker | Parts not printed; 0/8 actuators |
| Reuse potential | Costed BOM reusable as a cost anchor |

### C-4 · Dhruv's control path

| Field | Value |
| --- | --- |
| Hardware/source | None verified |
| Software/firmware | Python telemetry code — EXISTS |
| Command/input | RPi4 → I2C → PCA9685 → PWM → MG996R (PROVISIONAL — electronics not finalised, unexercised) |
| Execution | "NA" |
| Physical output | "NA" |
| Telemetry/log | EXTERNAL online dataset (torque etc.) — NOT robot telemetry |
| Interface | Provisional only; NO final BOM exists yet — by design, pending body completion |
| Video | None |
| Integration status | Live integration post testing on both prototypes |
| Blocker | No hardware; electronics not yet selected |
| Reuse potential | Telemetry code potentially reusable once fed real data |

### C-5 · Sarathi — Policy Enforcement Point

| Field | Value |
| --- | --- |
| Hardware/source | Software service — github.com/BHIV-Engineering-Exchange/bhiv-sarathi |
| Software/firmware | Go; DEPLOYED on Render |
| Command/input | POST /v1/enforce + 9 X-Sarathi-* headers + Ed25519 signature |
| Execution | VERIFIED LIVE — unsigned request → HTTP 400 ERR_INBOUND_SIGNATURE_MISSING |
| Physical/system output | Structured JSON verdict + error code |
| Telemetry/log | /metrics, /metrics/prometheus, /health/deep 3/3, router 4/4, uptime ~54 h |
| Interface | HTTPS/JSON — 9 endpoints verified live, 9 confirmed 404 (18 probed) |
| Video | PENDING (terminal capture) |
| Integration status | contract-only for hardware — total_routed: 0, no peer round-trip ever |
| Blocker | Onboarding/observe/ack routes not deployed; no device-side receiver |
| Reuse potential | HIGH — actuation authority + production-hardened execution webhook |

### C-6 · PIG — evidence spine

| Field | Value |
| --- | --- |
| Hardware/source | Python library, bhiv-ProjectIntelligenceGraph @ 411ba79 |
| Software/firmware | stdlib + jsonschema; pig CLI |
| Command/input | pytest tests -q · demo/run_demo.py · pig validate/replay/conformance/lookup/runtime/resolve/bench |
| Execution | 165 PASSED in 7.17s; demo completed |
| Physical/system output | Deterministic graph state; sha256 content hashes; tri-identity lookups |
| Telemetry/log | Observability module; pig bench reproducible |
| Interface | Python API + CLI; http_ingest.py generic PULL connector |
| Video | PENDING |
| Integration status | Library by design — correct end state |
| Blocker | Contract on unmerged branch; no host process owns it |
| Reuse potential | HIGH — WorkItem/Deliverable/EvidenceReference, bitemporal, replay-verified |

### C-7 · AQIAIC — reasoning engine

| Field | Value |
| --- | --- |
| Hardware/source | Python service @ 75dafc5 |
| Software/firmware | FastAPI; 36 endpoints |
| Command/input | python run_engine.py examples/payloads/sell_store_with_enwr.json |
| Execution | RAN TODAY |
| Physical/system output | dec_a24e0274..., STORE_WITH_ENWR, confidence 0.855, best/avg/worst, abstained:false |
| Telemetry/log | /metricz, /health, /livez, /readyz, /audit, /freshness |
| Interface | HTTP/JSON local — POST /decision, POST /aqiaic/plant/analyze (image upload), GET /aqiaic/pig/publish |
| Video | PENDING |
| Integration status | Production-ready, NOT deployed. Plant upstream = reference-standby |
| Blocker | Not deployed; thresholds uncalibrated |
| Reuse potential | HIGH — reasoning with honest abstention; PlantEvidence.kind already includes 'sensor' |

# 8.  TODAY'S REAL TARGET — the seven questions answered

| Question | Answer |
| --- | --- |
| Which robotics systems actually work? | NONE. Neither quadruped is assembled or powered. Both are pre-assembly by design stage |
| Which hardware components are operational? | None operational. But 30 printed structural components + 96 bolts physically exist and are PHOTO-VERIFIED, assembly-verified, classified "Not Operationally Tested" |
| Which control/telemetry interfaces exist? | On hardware: none exercised. PROVISIONAL only (RPi4→I2C→PCA9685→PWM→MG996R); electronics not finalised. On runtime: 7 live Sarathi routes verified, including a fail-closed enforcement gate |
| Which systems can communicate with BHIV runtime? | NO hardware can today. The runtime side is live and verified, but onboarding, observation-intake and acknowledgement routes return 404 — an edge node cannot register |
| What can genuinely be reused by VANA? | SOFTWARE: Sarathi (actuation authority + execution webhook), PIG (evidence spine), AQIAIC (reasoning with abstention). MECHANICAL: Manya's components, classified Potentially Reusable by their owner |
| What is still prototype-only? | Leg Assembly — Manya's own classification. Both quadrupeds as complete systems |
| What is missing? | 8 actuators · 8 parts to print · 96 nuts · ALL control electronics (MCU/battery/IMU/camera — now owned by Dhruv) · device-side webhook receiver · Sarathi edge routes · fleet device identity · PROCUREMENT OWNERSHIP |

# 9.  BLOCKERS AND DEPENDENCIES

| # | Blocker | Owner | Impact | Recovery |
| --- | --- | --- | --- | --- |
| 1 | 0 of 8 actuators (RX_64 x4, RX_28 x4) | Unassigned | Blocks gates 2–7 on both prototypes | Procure |
| 2 | Control electronics — MCU, battery, IMU, camera in no inventory | DHRUV (resolved today) | Blocked both prototypes permanently | Dhruv to state on-hand vs to-buy |
| 3 | 8 parts still to print + H-frame size/print-time constraint | Manya | Blocks leg assembly | Print queue |
| 4 | 96 M2.5 nuts | Suraj → procurement | Blocks assembly | Ordered per 08:05 instruction |
| 5 | Procurement ownership — budget, approver, lead time | UNASSIGNED (from Day 0) | Nothing can be bought | NEEDS AN OWNER |
| 6 | Sarathi edge routes 404 — evaluators/JWKS, observe, downstream-ack, audit | Hemanth | Edge node cannot register or return telemetry | Verify deployment version; redeploy |
| 7 | Device-side webhook receiver does not exist | Group 3 + 4 | No actuation path terminates on a device | Build |
| 8 | Device identity at fleet scale | Group 4 | Fleet deployment unsolved | Design decision |
| 9 | V0–V4 scale undefined | Ashmit (tooling-blocked) | No capability graded on intended scale | Define, or adopt the gate ladder |
| 10 | No runtime videos (rule 4) | All | Non-negotiable unmet | Record |
| 11 | No final electronics BOM exists — BY DESIGN: body first, BOM after | Dhruv | Control path cannot be verified until it is fixed | Sequenced — final BOM follows body completion |
| 12 | Torque check WHEN electronics are chosen — MG996R (~9–11 kg·cm, verify datasheet) sits well under the ~40/35 kg·cm design assumption | Dhruv | Would invalidate the load analysis IF MG996R is confirmed | Check at selection time — not urgent while provisional |

# 10.  TOMORROW'S CRITICAL PATH

Print the 8 outstanding parts → enables leg assembly → enables the mechanical-linkage verification Suraj specified (no actuators needed). The group's only route to a physical runtime artifact this week.

Assign procurement. Unresolved since Day 0 and gating everything physical.

Dhruv: electronics selection follows body completion (his stated sequence). When the parts are chosen, run the torque check against the actual actuator before ordering.

Record the outstanding videos (rule 4) — the cheapest compliance win available.

Verify the Sarathi deployment version. If Render runs an older build, redeploying restores edge onboarding and telemetry routes — my highest-value single action.

Define V0–V4, or adopt the gate ladder in §0 as the group scale.

Attempt the first two-system round-trip — AQIAIC GET /aqiaic/pig/publish → PIG http_ingest. Would be Group 3's first genuine INTEGRATION proof (gate 6).

# APPENDIX A — EVIDENCE REGISTER

| ID | Claim | Type | Artifact | Verdict |
| --- | --- | --- | --- | --- |
| E-1 | Printed structural components physically exist | PHOTOGRAPH x14, in-frame timestamps | manya-images/ | ACCEPTED |
| E-2 | Component status, assembly verification, reusability | Document | Mechanical Structural Verification.pdf | ACCEPTED |
| E-3 | Corrected quantities (Smaller Disc 4→0, lower link 4→2) | Document | updated inventory.pdf | ACCEPTED |
| E-4 | Arya's fastener spec = M3 | Owner statement from live assembly | Message | ACCEPTED |
| E-5 | Arya's assembly geometry | CAD RENDERS x4 | images/ | CAD only — NOT hardware |
| E-6 | Sarathi live + fail-closed | Captured HTTP | evidence/EDGE-RUNTIME-PROOF/ | ACCEPTED |
| E-7 | Sarathi edge routes not deployed | Captured probe, 10 endpoints | same | ACCEPTED |
| E-8 | PIG works — 165 tests + demo | Captured terminal | evidence/DAY2-RUNTIME/pig-proof.md | ACCEPTED |
| E-9 | AQIAIC produces real decisions | Captured terminal | evidence/DAY2-RUNTIME/aqiaic-proof.md | ACCEPTED |
| E-10 | BHIV repos unmodified by testing | git status = 24 / 10 | same | ACCEPTED |
| E-11 | Dhruv's control path | Owner statement | PROVISIONAL — no final BOM exists yet | NOT FINALISED (by design) |
| E-12 | Dhruv's telemetry evidence | EXTERNAL online dataset | Not supplied | NOT robot telemetry |
| E-13 | Tender imposes no motor restriction | Document read in full | Tender_Document_IS202600023301.pdf | ACCEPTED |
| E-14 | Any hardware powers on | — | NONE | NOT CLAIMED |

# APPENDIX B — TENDER REVIEW (closed on Suraj's instruction)

Read Tender_Document_IS202600023301.pdf (URSC / Dept. of Space, 52 pp.) in full. NO MOTOR RESTRICTIONS — none of the 12 technical specs mentions motors, actuators, servos, torque or drive type; it is a performance-based specification.

Suraj's response: "Right no motor restrictions. Tender filled already and that's a different story. This document was sent only to avoid confusion regarding why two separate BOM and prototypes." — CLOSED; no further action. Full analysis retained at findings/group3/TENDER_MOTOR_SPEC_ANALYSIS.md.

Every accepted claim has a captured artifact with the exact command or file behind it. My own errors are recorded in §6 rather than quietly amended.